## WBS
Alice WBS Id* | Name* | Level* | Code - read only
3837e7c2-0906-4333-ac9b-a2737d9ef3ab | Island 2026 | 1 | project
cbd410b2-5548-4cd2-8527-f2345a50d57f | SITE PREPARATION & DEMOLITION | 2 | project.SITE PREPARATION & DEMOLITION
0d25cbc5-489e-404b-bca9-c37d58b2aab2 | EARTHWORK & BASEMENT | 2 | project.EARTHWORK & BASEMENT
877325b6-0ec2-4dc8-b9e3-cfa6b8292d16 | SUPERSTRUCTURE | 2 | project.SUPERSTRUCTURE – ZONE A
63195f08-e779-4f3a-ae3a-306d40e10c1c | ENVELOPE | 2 | project.ENVELOPE
c3929e98-3e87-4181-a90c-ec2646e7d440 | MEP INSTALLATION | 2 | project.MEP INSTALLATION
da7c403f-4319-48fd-8009-37270386cab6 | INTERIOR | 2 | project.INTERIOR FINISHES
383f728a-1104-4558-be7b-db47650d4deb | COMMISSIONING & CLOSEOUT | 2 | project.COMMISSIONING & CLOSEOUT

## Tasks
Id* | Name* | Type* | Source* | External ID - read only | Alice Calendar Name | Duration equation | Is Continuous* | Task Status | Planned Start Date - read only | Planned End Date - read only | Planned Budgeted Labor Units - read only | Actual Start Date | Actual End Date | Actual Duration - read only | Remaining Duration - read only | Suspend Date - read only | Resume Date - read only | Earliest Start - read only | Earliest End - read only | Free slack (hours) - read only | Free slack (days) - read only | Total slack (hours) - read only | Total slack (days) - read only | Alice WBS Id* | Primary Constraint Type | Primary Constraint Date | Primary Constraint Time
A1070 | Install Construction Fencing | REGULAR | MANUAL |  | Default calendar | 24 | FALSE | NOT_STARTED | 2029-10-01T09:00 | 2029-10-03T17:00 | 0 | [6 empty] | 2029-10-01T09:00 | 2029-10-03T17:00 | 0 | 0 | 1480 | 185 | cbd410b2-5548-4cd2-8527-f2345a50d57f
A1080 | Install Site Office & Welfare Units | REGULAR | MANUAL |  | Default calendar | 32 | FALSE | NOT_STARTED | 2029-10-04T09:00 | 2029-10-09T17:00 | 0 | [6 empty] | 2029-10-04T09:00 | 2029-10-09T17:00 | 1528 | 191 | 1528 | 191 | cbd410b2-5548-4cd2-8527-f2345a50d57f
A1090 | Temporary Water Installation | REGULAR | MANUAL |  | Default calendar | 24 | FALSE | NOT_STARTED | 2029-10-04T09:00 | 2029-10-08T17:00 | 0 | [6 empty] | 2029-10-04T09:00 | 2029-10-08T17:00 | 1536 | 192 | 1536 | 192 | cbd410b2-5548-4cd2-8527-f2345a50d57f
A1100 | Temporary Power Installation | REGULAR | MANUAL |  | Default calendar | 32 | FALSE | NOT_STARTED | 2029-10-04T09:00 | 2029-10-09T17:00 | 0 | [6 empty] | 2029-10-04T09:00 | 2029-10-09T17:00 | 1528 | 191 | 1528 | 191 | cbd410b2-5548-4cd2-8527-f2345a50d57f
A1110 | Tree Removal & Clearing | REGULAR | MANUAL |  | Default calendar | 40 | FALSE | NOT_STARTED | 2029-10-04T09:00 | 2029-10-10T17:00 | 0 | [6 empty] | 2029-10-04T09:00 | 2029-10-10T17:00 | 0 | 0 | 1480 | 185 | cbd410b2-5548-4cd2-8527-f2345a50d57f
A1120 | Bleacher Demolition | REGULAR | MANUAL |  | Default calendar | 56 | FALSE | NOT_STARTED | 2029-10-04T09:00 | 2029-10-12T17:00 | 0 | [6 empty] | 2029-10-04T09:00 | 2029-10-12T17:00 | 1504 | 188 | 1504 | 188 | cbd410b2-5548-4cd2-8527-f2345a50d57f
A1140 | Crane Pad Construction | REGULAR | MANUAL |  | Default calendar | 40 | FALSE | NOT_STARTED | 2029-10-11T09:00 | 2029-10-17T17:00 | 0 | [6 empty] | 2029-10-11T09:00 | 2029-10-17T17:00 | 1480 | 185 | 1480 | 185 | cbd410b2-5548-4cd2-8527-f2345a50d57f
A1150 | Laydown Area Preparation | REGULAR | MANUAL |  | Default calendar | 0 | FALSE | NOT_STARTED | 2029-10-11T09:00 | 2029-10-11T09:00 | 0 | [6 empty] | 2029-10-11T09:00 | 2029-10-11T09:00 | 1520 | 190 | 1519 | 190 | cbd410b2-5548-4cd2-8527-f2345a50d57f
A1170 | Full Basement Excavation | REGULAR | MANUAL |  | Default calendar | 56 | FALSE | NOT_STARTED | 2029-10-01T09:00 | 2029-10-09T17:00 | 0 | [6 empty] | 2029-10-01T09:00 | 2029-10-09T17:00 | 0 | 0 | 0 | 0 | 0d25cbc5-489e-404b-bca9-c37d58b2aab2
A1180 | Shoring / Stabilization | REGULAR | MANUAL |  | Default calendar | 40 | FALSE | NOT_STARTED | 2029-10-10T09:00 | 2029-10-16T17:00 | 0 | [6 empty] | 2029-10-10T09:00 | 2029-10-16T17:00 | 1488 | 186 | 1488 | 186 | 0d25cbc5-489e-404b-bca9-c37d58b2aab2
A1190 | Subgrade Preparation | REGULAR | MANUAL |  | Default calendar | 32 | FALSE | NOT_STARTED | 2029-10-10T09:00 | 2029-10-15T17:00 | 0 | [6 empty] | 2029-10-10T09:00 | 2029-10-15T17:00 | 0 | 0 | 0 | 0 | 0d25cbc5-489e-404b-bca9-c37d58b2aab2
A1200 | Footings – Form/Rebar/Pour | REGULAR | MANUAL |  | Default calendar | 80 | FALSE | NOT_STARTED | 2029-10-16T09:00 | 2029-10-29T17:00 | 0 | [6 empty] | 2029-10-16T09:00 | 2029-10-29T17:00 | 0 | 0 | 0 | 0 | 0d25cbc5-489e-404b-bca9-c37d58b2aab2
A1210 | Grade Beams | REGULAR | MANUAL |  | Default calendar | 56 | FALSE | NOT_STARTED | 2029-11-08T09:00 | 2029-11-16T17:00 | 0 | [6 empty] | 2029-11-08T09:00 | 2029-11-16T17:00 | 0 | 0 | 0 | 0 | 0d25cbc5-489e-404b-bca9-c37d58b2aab2
A1220 | Basement Retaining Walls | REGULAR | MANUAL |  | Default calendar | 24 | FALSE | NOT_STARTED | 2029-11-19T09:00 | 2029-11-21T17:00 | 0 | [6 empty] | 2029-11-19T09:00 | 2029-11-21T17:00 | 0 | 0 | 0 | 0 | 0d25cbc5-489e-404b-bca9-c37d58b2aab2
A1230 | Waterproofing & Drainage | REGULAR | MANUAL |  | Default calendar | 40 | FALSE | NOT_STARTED | 2029-11-22T09:00 | 2029-11-28T17:00 | 0 | [6 empty] | 2029-11-22T09:00 | 2029-11-28T17:00 | 0 | 0 | 0 | 0 | 0d25cbc5-489e-404b-bca9-c37d58b2aab2
A1240 | Basement Slab on Grade | REGULAR | MANUAL |  | Default calendar | 56 | FALSE | NOT_STARTED | 2029-12-17T09:00 | 2029-12-25T17:00 | 0 | [6 empty] | 2029-12-17T09:00 | 2029-12-25T17:00 | 0 | 0 | 0 | 0 | 0d25cbc5-489e-404b-bca9-c37d58b2aab2
A1250 | Underground Utilities | REGULAR | MANUAL |  | Default calendar | 56 | FALSE | NOT_STARTED | 2029-11-29T09:00 | 2029-12-07T17:00 | 0 | [6 empty] | 2029-11-29T09:00 | 2029-12-07T17:00 | 0 | 0 | 0 | 0 | 0d25cbc5-489e-404b-bca9-c37d58b2aab2
A1260 | Backfill & Compaction | REGULAR | MANUAL |  | Default calendar | 40 | FALSE | NOT_STARTED | 2029-12-10T09:00 | 2029-12-14T17:00 | 0 | [6 empty] | 2029-12-10T09:00 | 2029-12-14T17:00 | 0 | 0 | 0 | 0 | 0d25cbc5-489e-404b-bca9-c37d58b2aab2
A1270 | Foundational Columns | REGULAR | MANUAL |  | Default calendar | 56 | FALSE | NOT_STARTED | 2029-10-30T09:00 | 2029-11-07T17:00 | 0 | [6 empty] | 2029-10-30T09:00 | 2029-11-07T17:00 | 0 | 0 | 0 | 0 | 0d25cbc5-489e-404b-bca9-c37d58b2aab2
A1330 | Frame: Columns | REGULAR | MANUAL |  | Default calendar | 48 | FALSE | NOT_STARTED | 2030-01-08T09:00 | 2030-01-15T17:00 | 0 | [6 empty] | 2030-01-08T09:00 | 2030-01-15T17:00 | 0 | 0 | 0 | 0 | 877325b6-0ec2-4dc8-b9e3-cfa6b8292d16
A1340 | Floor | REGULAR | MANUAL |  | Default calendar | 24 | FALSE | NOT_STARTED | 2030-01-03T09:00 | 2030-01-07T17:00 | 0 | [6 empty] | 2030-01-03T09:00 | 2030-01-07T17:00 | 0 | 0 | 0 | 0 | 877325b6-0ec2-4dc8-b9e3-cfa6b8292d16
A1350 | Frame: Beams | REGULAR | MANUAL |  | Default calendar | 48 | FALSE | NOT_STARTED | 2029-12-26T09:00 | 2030-01-02T17:00 | 0 | [6 empty] | 2029-12-26T09:00 | 2030-01-02T17:00 | 0 | 0 | 0 | 0 | 877325b6-0ec2-4dc8-b9e3-cfa6b8292d16
A1420 | Roof | REGULAR | MANUAL |  | Default calendar | 32 | FALSE | NOT_STARTED | 2030-01-16T09:00 | 2030-01-21T17:00 | 0 | [6 empty] | 2030-01-16T09:00 | 2030-01-21T17:00 | 0 | 0 | 0 | 0 | 877325b6-0ec2-4dc8-b9e3-cfa6b8292d16
A1590 | Facade Install + Glazing | REGULAR | MANUAL |  | Default calendar | 256 | FALSE | NOT_STARTED | 2030-01-22T09:00 | 2030-03-06T17:00 | 0 | [6 empty] | 2030-01-22T09:00 | 2030-03-06T17:00 | 0 | 0 | 0 | 0 | 63195f08-e779-4f3a-ae3a-306d40e10c1c
A1670 | Mechanical Room Buildout | REGULAR | MANUAL |  | Default calendar | 112 | FALSE | NOT_STARTED | 2030-03-07T09:00 | 2030-03-26T17:00 | 0 | [6 empty] | 2030-03-07T09:00 | 2030-03-26T17:00 | 568 | 71 | 568 | 71 | c3929e98-3e87-4181-a90c-ec2646e7d440
A1680 | Main Electrical & Riser Install | REGULAR | MANUAL |  | Default calendar | 112 | FALSE | NOT_STARTED | 2030-03-07T09:00 | 2030-03-26T17:00 | 0 | [6 empty] | 2030-03-07T09:00 | 2030-03-26T17:00 | 0 | 0 | 184 | 23 | c3929e98-3e87-4181-a90c-ec2646e7d440
A1690 | MEP Rough-In | REGULAR | MANUAL |  | Default calendar | 384 | FALSE | NOT_STARTED | 2030-03-27T09:00 | 2030-05-31T17:00 | 0 | [6 empty] | 2030-03-27T09:00 | 2030-05-31T17:00 | 184 | 23 | 184 | 23 | c3929e98-3e87-4181-a90c-ec2646e7d440
A1740 | Interior Framing | REGULAR | MANUAL |  | Default calendar | 96 | FALSE | NOT_STARTED | 2030-03-07T09:00 | 2030-03-22T17:00 | 0 | [6 empty] | 2030-03-07T09:00 | 2030-03-22T17:00 | 0 | 0 | 0 | 0 | da7c403f-4319-48fd-8009-37270386cab6
A1750 | Drywall & Finishes | REGULAR | MANUAL |  | Default calendar | 192 | FALSE | NOT_STARTED | 2030-03-25T09:00 | 2030-04-25T17:00 | 0 | [6 empty] | 2030-03-25T09:00 | 2030-04-25T17:00 | 0 | 0 | 0 | 0 | da7c403f-4319-48fd-8009-37270386cab6
A1760 | Ceiling Installation | REGULAR | MANUAL |  | Default calendar | 128 | FALSE | NOT_STARTED | 2030-04-26T09:00 | 2030-05-17T17:00 | 0 | [6 empty] | 2030-04-26T09:00 | 2030-05-17T17:00 | 0 | 0 | 0 | 0 | da7c403f-4319-48fd-8009-37270386cab6
A1820 | MEP Start-Up | REGULAR | MANUAL |  | Default calendar | 56 | FALSE | NOT_STARTED | 2030-05-20T09:00 | 2030-05-28T17:00 | 0 | [6 empty] | 2030-05-20T09:00 | 2030-05-28T17:00 | 0 | 0 | 0 | 0 | 383f728a-1104-4558-be7b-db47650d4deb
A1830 | TAB | REGULAR | MANUAL |  | Default calendar | 56 | FALSE | NOT_STARTED | 2030-05-29T09:00 | 2030-06-06T17:00 | 0 | [6 empty] | 2030-05-29T09:00 | 2030-06-06T17:00 | 0 | 0 | 0 | 0 | 383f728a-1104-4558-be7b-db47650d4deb
A1840 | Integrated Systems Testing | REGULAR | MANUAL |  | Default calendar | 40 | FALSE | NOT_STARTED | 2030-06-07T09:00 | 2030-06-13T17:00 | 0 | [6 empty] | 2030-06-07T09:00 | 2030-06-13T17:00 | 0 | 0 | 0 | 0 | 383f728a-1104-4558-be7b-db47650d4deb
A1860 | Final Inspections | REGULAR | MANUAL |  | Default calendar | 40 | FALSE | NOT_STARTED | 2030-05-20T09:00 | 2030-05-24T17:00 | 0 | [6 empty] | 2030-05-20T09:00 | 2030-05-24T17:00 | 224 | 28 | 224 | 28 | 383f728a-1104-4558-be7b-db47650d4deb
A1880 | Hurricane Contingency Buffer | REGULAR | MANUAL |  | Default calendar | 112 | FALSE | NOT_STARTED | 2030-06-14T09:00 | 2030-07-03T17:00 | 0 | [6 empty] | 2030-06-14T09:00 | 2030-07-03T17:00 | 0 | 0 | 0 | 0 | 383f728a-1104-4558-be7b-db47650d4deb

## Task Relationships
From Task Id* | To Task Id* | Type* | Lag
A1070 | A1080 | FS | 0
A1070 | A1090 | FS | 0
A1070 | A1100 | FS | 0
A1070 | A1110 | FS | 0
A1070 | A1120 | FS | 0
A1110 | A1140 | FS | 0
A1110 | A1150 | FS | 0
A1170 | A1180 | FS | 0
A1170 | A1190 | FS | 0
A1190 | A1200 | FS | 0
A1200 | A1270 | FS | 0
A1210 | A1220 | FS | 0
A1220 | A1230 | FS | 0
A1230 | A1250 | FS | 0
A1240 | A1350 | FS | 0
A1250 | A1260 | FS | 0
A1260 | A1240 | FS | 0
A1270 | A1210 | FS | 0
A1330 | A1420 | FS | 0
A1340 | A1330 | FS | 0
A1340 | A1420 | FS | 0
A1350 | A1340 | FS | 0
A1420 | A1590 | FS | 0
A1590 | A1670 | FS | 0
A1590 | A1680 | FS | 0
A1590 | A1690 | FS | 0
A1590 | A1740 | FS | 0
A1680 | A1690 | FS | 0
A1740 | A1750 | FS | 0
A1750 | A1760 | FS | 0
A1760 | A1820 | FS | 0
A1760 | A1860 | FS | 0
A1820 | A1830 | FS | 0
A1830 | A1840 | FS | 0
A1840 | A1880 | FS | 0

## Crews
Name* | Name Snake Case - read only | Available quantity | Default quantity | Persons per crew* | Cost per person per hr - read only | Cost per crew per hr* | Calendar* | Idle Cost Enabled* | External id - read only | Subcontractor name - read only | Ramp Resource* | Color
Commissioning / Controls Support | commissioning_controls_support | 1 | 1 | 3 | 100 | 300 | Default calendar | FALSE |  |  | FALSE | #fc5555
Commissioning Crew | commissioning_crew | 1 | 1 | 3 | 80 | 240 | Default calendar | FALSE |  |  | FALSE
Concrete Crew | concrete_crew | 1 | 1 | 8 | 65 | 520 | Default calendar | FALSE |  |  | FALSE | #fea4a4
Concrete Topping Crew | concrete_topping_crew | 1 | 1 | 7 | 70 | 490 | Default calendar | FALSE |  |  | FALSE | #f4c2fe
Core Crew | core_crew | 1 | 1 | 8 | 70 | 560 | Default calendar | FALSE |  |  | FALSE | #79f6f6
Deck Install Crew | deck_install_crew | 1 | 1 | 5 | 70 | 350 | Default calendar | FALSE |  |  | FALSE | #cdc3fe
Demolition Crew (bleachers) | demolition_crew_bleachers_ | 1 | 1 | 4 | 80 | 320 | Default calendar | FALSE |  |  | FALSE | #6549f3
Drywall Robot Crew | drywall_robot_crew | 2 | 1 | 4 | 0 | 0 | Default calendar | FALSE |  |  | FALSE | #fc5555
Earthwork Crew | earthwork_crew | 2 | 1 | 6 | 0 | 0 | 5dx10hr | FALSE |  |  | FALSE | #67cc5c
Earthwork Crew (excavation) | earthwork_crew_excavation_ | 1 | 1 | 3 | 120 | 360 | Default calendar | FALSE |  |  | FALSE | #ce6fe2
Electrical Rough-In Crew | electrical_rough_in_crew | 1 | 1 | 6 | 80 | 480 | Default calendar | FALSE |  |  | FALSE | #fc5555
Exc | exc | 1 | 1 | 3 | 100 | 300 | Default calendar | FALSE |  |  | FALSE | #a5fd9b
Facade Install Crew | facade_install_crew | 1 | 1 | 6 | 75 | 450 | Default calendar | FALSE |  |  | FALSE | #fc5555
Facade Install Crew 1 | facade_install_crew_1 | 1 | 1 | 6 | 75 | 450 | Default calendar | FALSE |  |  | FALSE | #fc5555
Facade Install Crew 2 | facade_install_crew_2 | 1 | 1 | 6 | 75 | 450 | Default calendar | FALSE |  |  | FALSE | #fc5555
Facade Robot Crew | facade_robot_crew | 1 | 1 | 4 | 0 | 0 | Default calendar | TRUE |  |  | FALSE | #fc5555
Finishes Crew | finishes_crew | 1 | 1 | 6 | 55 | 330 | Default calendar | FALSE |  |  | FALSE
Flooring Crew | flooring_crew | 1 | 1 | 4 | 65 | 260 | Default calendar | FALSE |  |  | FALSE | #fc5555
HVAC Rough-In Crew | hvac_rough_in_crew | 1 | 1 | 6 | 75 | 450 | Default calendar | FALSE |  |  | FALSE | #fc5555
Interior Framing Crew | interior_framing_crew | 1 | 1 | 6 | 60 | 360 | Default calendar | FALSE |  |  | FALSE
Interior Framing/Drywall Crew | interior_framing_drywall_crew | 2 | 1 | 6 | 60 | 360 | Default calendar | FALSE |  |  | FALSE | #fc5555
Interiors Crew | interiors_crew | 1 | 1 | 4 | 65 | 260 | Default calendar | FALSE |  |  | FALSE | #fc5555
MEP Rough-In Crew | mep_rough_in_crew | 1 | 1 | 8 | 75 | 600 | Default calendar | FALSE |  |  | FALSE
Mobile Crane | mobile_crane | 1 | 1 | 1 | 250 | 250 | Default calendar | TRUE |  |  | FALSE | #fc5555
Plumbing + Fire Protection Rough-In Crew | plumbing_fire_protection_rough_in_crew | 1 | 1 | 6 | 75 | 450 | Default calendar | FALSE |  |  | FALSE | #fc5555
Pour Strip Closure Crew | pour_strip_closure_crew | 1 | 1 | 8 | 70 | 560 | Default calendar | FALSE |  |  | FALSE | #f679af
Rebar Crew | rebar_crew |  | 1 | 1 | 2 | 2 | 5dx10hr | TRUE |  |  | FALSE | #fc5555
Roofing Crew | roofing_crew | 1 | 1 | 6 | 65 | 390 | Default calendar | FALSE |  |  | FALSE | #fc5555
Shoring / Stabilization Crew | shoring_stabilization_crew | 1 | 1 | 4 | 90 | 360 | Default calendar | FALSE |  |  | FALSE | #d8317a
Site Setup Crew | site_setup_crew | 1 | 1 | 4 | 60 | 240 | Default calendar | FALSE |  |  | FALSE | #fc8c55
Steel Erection Crew | steel_erection_crew | 1 | 1 | 6 | 70 | 420 | Default calendar | FALSE |  |  | FALSE
Steel Fabrication Crew | steel_fabrication_crew | 1 | 1 | 6 | 70 | 420 | Default calendar | FALSE |  |  | FALSE
Structural Crew | structural_crew | 1 | 1 | 6 | 70 | 420 | Default calendar | FALSE |  |  | FALSE | #a5d1fd
TAB Team | tab_team | 1 | 1 | 3 | 100 | 300 | Default calendar | FALSE |  |  | FALSE | #fc5555
Temp Power/Electrical | temp_power_electrical | 1 | 1 | 2 | 90 | 180 | Default calendar | FALSE |  |  | FALSE | #fdd50d
Temp Water/Plumbing | temp_water_plumbing | 1 | 1 | 2 | 85 | 170 | Default calendar | TRUE |  |  | FALSE | #45c4c4
Tree Removal / Clearing Crew | tree_removal_clearing_crew | 1 | 1 | 3 | 80 | 240 | Default calendar | FALSE |  |  | FALSE | #4ba3fc
Underground Utilities Crew | underground_utilities_crew | 1 | 1 | 4 | 80 | 320 | Default calendar | FALSE |  |  | FALSE | #feea86
Waterproofing & Drainage Crew | waterproofing_drainage_crew | 1 | 1 | 4 | 70 | 280 | Default calendar | FALSE |  |  | FALSE | #e4cbbe

## Task Crews
Task Id* | Alice Crew Name* | Is Primary* | Required Amount | Required Min. | Required Max. | Required Actual | Required Remaining
A1070 | Site Setup Crew | TRUE | 1
A1080 | Site Setup Crew | TRUE | 1
A1090 | Site Setup Crew | FALSE | 1
A1100 | Site Setup Crew | FALSE | 1
A1110 | Tree Removal / Clearing Crew | TRUE | 1
A1120 | Demolition Crew (bleachers) | TRUE | 1
A1140 | Site Setup Crew | FALSE | 1
A1150 | Site Setup Crew | TRUE | 1
A1170 | Earthwork Crew (excavation) | TRUE | 1
A1180 | Shoring / Stabilization Crew | TRUE | 1
A1190 | Earthwork Crew (excavation) | TRUE | 1
A1200 | Concrete Crew | TRUE | 1
A1210 | Concrete Crew | TRUE | 1
A1220 | Concrete Crew | TRUE | 1
A1230 | Earthwork Crew (excavation) | FALSE | 1
A1240 | Concrete Crew | TRUE | 1
A1250 | Underground Utilities Crew | TRUE | 1
A1260 | Earthwork Crew (excavation) | FALSE | 1
A1260 | Exc | FALSE | 1
A1270 | Concrete Crew | FALSE | 1
A1330 | Structural Crew | FALSE | 1
A1340 | Structural Crew | FALSE | 1
A1420 | Structural Crew | FALSE | 1
A1590 | Facade Install Crew | FALSE | 1
A1670 | HVAC Rough-In Crew | TRUE | 1
A1680 | Electrical Rough-In Crew | TRUE | 1
A1690 | Electrical Rough-In Crew | FALSE | 1
A1690 | HVAC Rough-In Crew | TRUE | 1
A1690 | Plumbing + Fire Protection Rough-In Crew | FALSE | 1
A1740 | Interiors Crew | FALSE | 1
A1750 | Interiors Crew | FALSE | 1
A1760 | Interiors Crew | TRUE | 1
A1820 | Commissioning / Controls Support | TRUE | 1
A1820 | Electrical Rough-In Crew | FALSE | 1
A1820 | HVAC Rough-In Crew | FALSE | 1
A1820 | Plumbing + Fire Protection Rough-In Crew | FALSE | 1
A1830 | TAB Team | TRUE | 1
A1840 | Commissioning / Controls Support | TRUE | 1
A1840 | Electrical Rough-In Crew | FALSE | 1
A1840 | HVAC Rough-In Crew | FALSE | 1
A1840 | Plumbing + Fire Protection Rough-In Crew | FALSE | 1
A1860 | Commissioning / Controls Support | TRUE | 1

## Materials
Name* | Name Snake Case - read only | Type* | Available quantity | Cost per unit* | External id - read only | Color
Total Cost | total_cost | CONSUMABLE | 999999 | 0

## Task Materials
Task Id* | Alice Material Name* | Required Amount* | Supplies

## Equipment
Name* | Name Snake Case - read only | Available quantity | Cost per hr* | Idle Cost Enabled* | External id - read only | Idle Cost per hr | Idle Time Calendar | Ramp Resource* | Color
Compactor/Roller | compactor_roller | 1 | 0 | FALSE |  |  | 5dx10hr | FALSE
Concrete Pump | concrete_pump | 1 | 0 | FALSE |  |  | 5dx10hr | FALSE
Dozer | dozer | 1 | 0 | FALSE |  |  | 5dx10hr | FALSE
Dump Truck | dump_truck | 4 | 0 | FALSE |  |  | 5dx10hr | FALSE
Excavator | excavator | 2 | 0 | FALSE |  |  | 5dx10hr | FALSE
Forklift / Telehandler | forklift_telehandler | 2 | 0 | FALSE |  |  | 5dx10hr | FALSE
Mobile Crane | mobile_crane | 1 | 0 | FALSE |  | 0 | 5dx10hr | FALSE | #a5fd9b
Scissor Lift | scissor_lift | 4 | 0 | FALSE |  |  | 5dx10hr | FALSE

## Task Equipment
Task Id* | Alice Equipment Name* | Required Amount*
A1170 | Excavator | 1
A1190 | Compactor/Roller | 1
A1200 | Concrete Pump | 1
A1220 | Concrete Pump | 1
A1260 | Compactor/Roller | 1
A1330 | Mobile Crane | 1
A1340 | Mobile Crane | 1
A1420 | Mobile Crane | 1
A1590 | Mobile Crane | 1

## Production Rate
Name* | Name snake Case - read only | Qty/Hr*
Backfill/Compaction (cy/hr) | backfill_compaction_cy_hr_ | 35
MEP Rough-In per Trade (sf/hr) | mep_rough_in_per_trade_sf_hr_ | 200
Hauling (cy/hr) | hauling_cy_hr_ | 30
Interior (sf/hr) | interior_sf_hr_ | 250
Excavation (cy/hr) | excavation_cy_hr_ | 40
Proofroll (sf/hr) | proofroll_sf_hr_ | 2000
Slab-on-Grade (sf/hr) | slab_on_grade_sf_hr_ | 300

## Ramp Resource
Resource Name* | Type* | From* | Capacity